## Sheet1
Commitment 1:Employ innovation and technology to ensure adolescents and youth attain the highest possible standard of health
Perfomance trends of key indicators, 2021/22 to 2025/26
Key Actions/Activities | Indicator | Timeline | 2021/2022 | 2022/2023 | 2023/2024 | 2024/2025 | 2025/2026 | Cumulative (2019-2026) |  | Responsibility | Budget | Expenditure (2025- 2026) | Remarks
[8 empty] | Cumulative.Achievements | Cumulative. Targets (25-26)
Objective 1:Improve health of adolescents and youth to the highest possible standard
Establishment of Constituency Innovation Hubs (CIHs) centres to facilitate access to life skills education, entrepreneurship training, SRH education | No. Constituency Innovation Hubs established |  | 4 | 25 | 12 | 0 |  | 41 | 12 | MoH | 4B
Establishment of the Youth Empowerment Centres (YECs) to facilitate access to lifeskills, HIV-AIDS prevention , Sexual Reproductive Health (SRH) services | -No of youth empowerment centers established | [6 empty] | 0 | - | MoH
Develop applications for youth friendly Sexual Reproductive Health (SRH) information | No. of applications developed |  | - | 1 | 2 | - |  | 3 | - | MoH | 2B
| No. of adolescents and youth reached with correct information on SRH/HIV/Teenage pregnancy/SGBV through innovative and digital platform | [6 empty] | 0 |  | MoH
Increase access to SRH /HIV information by adolescents and youth through innovative and digital platforms e.g Peer to peer, webinars, X space... | [7 empty] | 0 |  | MoH
Integrate and nurture AYS- RHR related social enterprises and innovations in SRH programming at all levels | No. of enterprises and innovations integrated and nurtured |  | - | - | 0 | 0 |  | 0 | 60 | MoH | 30M
Finalisation and implement strategic MOH policies (RH policy and RH commodity security strategy) and dissemination at all levels No. of policies finalised and being implemented Develop MOH Policies, guideline, strategies standards related to SRH services | No. of policies finalized, disseminated and being implemented |  | 1 |  | - | 1 |  | 2 | 2 | MoH | 20M
Conduct education and demand creation at community level for SRH interventions including abstinence for minors | No. of community level education and demand creation forums held | [6 empty] | 0 | 5 | MoH | 60M
Advocate for integration of comprehensive SRH services in UHC package | No. of advocacy forums held | [6 empty] | 0 | 5 | MoH | 500M
Establishment operationalize multi-sectorial collaboration workig group at National and County level(health,youth,education) and harmonization of policies. | No of established operational working groups |  |  |  |  | 48 |  | 48 | - | MoH | 0.5M
Operationalization of AYP Multisectoral Thematic working Group (TWGs) in National and Counties | No. of Functional AYP TWG in National and Counties | [6 empty] | 0 |  | MoH
Objective 2: Eliminate teenage pregnancies by 2030 | [7 empty] | 0 |  | MoH
Develop and implement a health sector response action plan for teenage pregnancy | Health sector response action plan report |  | 1 | 0 | - | 1 |  | 2 | 5 | MoH
Reduce teenage pregancies | Proportion of adolescents (10–19) attending ANC | [6 empty] | 0 |  | MoH
Develop and implement strategies to increase access to age-appropriate information/life skills including advocacy for abstinence for adolescents and young people in and out of school using multiple approaches | No. of strategies developed and being implemented |  | 1 | 0 | 1 | 1 |  | 3 | 1 | MoH
Develop and implement SRH care giver capacity building and support mechanism for care givers handling adolescents and young people in and out of school using multiple approaches and stakeholders capacity building of SRH Care givers on handling adolescents and young people in and out of school using multiple approaches and stakeholders | Caregiver guide developed No.of Caregivers Trained on SRH Services |  | - | 1 |  | 0 |  | 1 | 1 | MoH
Increase access to adolescent and youth friendly health services and support for school re-entry and services for ﬁrst time mothers | No. of youth accessing youth friendly health services |  | 1731174 | 261022 | 246234 | 1831313 |  | 4069743 | 400000 | MoH
Increase access to adolescent and youth friendly health services | [7 empty] | 0 |  | MoH
Develop a health sector adolescent SRH service segmentation SOP/guideline to fast enhance individualized quality access to services to adolescents and youth | Health sector adolescent SRH service segmentation SOP/guideline |  | - | - | - | 1 |  | 1 | 1 | MoH
Generate and disseminate evidence on context speciﬁc interventions that reduce and mitigate the impact of teenage pregnancy | Evidence generated and disseminated biannually |  | - | 1 | - | 1 |  | 2 | 3 | MoH